## 18Apr-19Apr
				TAD Test Report 18/04/2016 to 19/04/2016

Sr.No	Time	Status	Bug	Action	Status

1	7.15pm-2.40am	working fine	-	-	-

2	2.40am onwords	not uploading data	MQTT connection faluire	Power ON the Device again	Uploading data
				Added software code to reboot ESP when it is not able to connect to MQTT Server

## 19Apr-20Apr
				TAD Test Report 19/04/2016 to 20/04/2016

Sr.No	Time	Status	Bug	Action	Status

1	11am-2am	working fine	-	-	-

2	2am onwords	not uploading data	MQTT connection faluire	Keeping Device On, we have disconnected TATA docomo dongle and connected again	Uploading data
				We added ESP restart to solve this but it didn't work.

## 20Apr-21Apr
				TAD Test Report 20/04/2016 to 21/04/2016

Sr.No	Time	Device Under Test	Status	Bug	Action	Status

1	8pm – 11.30am	TADPUSH	working fine	-	Connected D-Link Wifi Dongle to ESP ( instead of Tata Docomo)	-

2	10am-1.30am	TADPUSH_LaVella	working fine	-	Connected to A4-Skynet WiFi	-

## 25Apr-27Apr
				TAD Test Report 25/04/2016 to 27/04/2016

Sr.No	Device Under Test	Bug	Cause	Action	Status

1	Kasturkunj	getting deviations in distance value from sensor	HCSR-04 requires 30 degree measuring angle to get best readings.	Tested Sensor in pantry area on flat suface which is giving correct values.	-
2	LaVella
				Now we need to test unit on actual site to verify the solution.	Testing Successful

## 28Apr-29Apr
		Deployed TAD at Kasturkunj on 28th April 2016		TAD Test Report 28/04/2016 to 29/04/2016

Sr.No	Device Under Test	Status	Bug	Solution

1	Kasturkunj (On Site)	Working Properly	Showing Spikes sometimes	Filter out wrong readings at Unit side or Server Side
2